## Test Case Format
Sr.No | Scenario Id | Scenario objective | Test Case Id | Test case Objective | Steps | Test Data | Expected Result | Actual Result | Status | Tester Name | Remark
1 | sc_01 |  | tc_001 | in account details or verification there is not limits for adhaar no or its not in integers form | seller verification 2 step | adhaar card : 1111Ab | they should be give limit and in integer form | it aacepted all and pass the data | Done | mayur
2 |  |  | tc_002 | personal data not save properly | seller profile | All verifcation details | it should saved data properly | it show error | not Done | ayush
3 | sc_02 |  | tc_003 | file is not attache | on dash board | on dashboard feature not work | they should attached there file | feature not work | not work | mayur
4 | sc_03 |  | tc_004 | in support there is not help center | on dash board | on help center | they should give info | no written details | not Done | ayush
5 | sc_04 |  | tc_005 | categories not work | on dash board | categoriess | they shoull upload all photos and details | feature not working | not work | Both

## Bug Report
Sc_ID | TC_ID | User Type | Bug Id | Bug Description | Feature Name | Page Name | Priority | Allocated To | Developer Status | Tester Status | Tester Name | Remark
sc_01 | TC_01 | User | bug_01 | in account details or verification there is not limits for adhaar no or its not in integers form | seller verification 2 step | verification | P1 |  | Completed | Fail | Mayur
sc_02 | TC_02 | User | bug_02 | personal data not save properly | All verifcation details | profile page | P2 |  | Completed | Fail | Ayush
sc_03 | TC_03 | User | bug_03 | file is not attache | on dashboard feature not work | on dash board | P3 |  | Completed | Fail | Mayur
sc_04 | TC_04 | User | bug_04 | in support there is not help center | on help centre | on dash board | P4 |  | Completed | Fail | Ayush
sc_05 | TC_05 | User | bug_05 | categories not work | categoriess | on dash board | P5 |  |  | fail | BOTH
sc_06 | TC_06 | user | bug_06 | ther is no specification on password e.g special caracter ,strong password | login password | on login page | P6 |  |  | fail | BOTH